## Sheet1
Iteration #1 | Feature | Feature | Feature | Feature
Date of milestone | 2016-12-09 | 2016-12-09 | 2016-12-09 | 2016-12-09
Features in scope | Join Game | Create Game | Movement | Login
Features implemented | Join Game | Create Game | Movement
Features in deficit this Iteration |  |  |  | Login
Iteration Comments & Summary | Player is able to join game through lan and multiplayer. | Player is able to create game through lan and multiplayer. | Player can move in the world | No login yet, google play might take longer to implement or make own database.
Iteration #2
Date of milestone | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07
Features in scope | Inventory | Equipment/Items | Login | Gameplay
Features implemented | Inventory | Equipment/Items | Login
Features in deficit this Iteration |  |  |  | Gameplay
Iteration Comments & Summary | The inventory syncs with the database and each user gets to see his own inventory. | Similar to Inventory just need to implement more different items. | Different players can login. | Was unable to develop more of the gameplay as it took some time to develop the database for the inventory.
Iteration #3
Date of milestone | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05
Features in scope | Gameplay | Equiping Weapons | Dropping Items | More Enemies
Features implemented | Gameplay | Equiping Weapons
Features in deficit this Iteration |  |  | Dropping Items | More Enemies
Iteration Comments & Summary | Gameplay is progressing there can still be more done. | The player can equip weapons in the inventory. | Need to finish implementing enemies and have them drop things | Need to implement some more enemies
Iteration #4
Date of milestone | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22
Features in scope | Dropping Items | More Enemies | Sounds | More Levels
Features implemented | Dropping Items
Features in deficit this Iteration |  | More Enemies | Sounds | More Levels
Iteration Comments & Summary | Items are dropped by enemies randomly | Started making more interesting enemies | Need to make/find some sounds | Need to implement more areas for players to explore
Iteration #5
Date of milestone | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05
Features in scope | Multiplayer Gameplay | More Enemies | Sounds | More Levels | Leveling up
Features implemented | Multiplayer Gameplay |  |  |  | Leveling up
Features in deficit this Iteration |  | More Enemies | Sounds | More Levels
Iteration Comments & Summary | The Host and Joined player can see eachothers actions | Working on more interesting enemies | Working on sounds to be heard by all players | More Levels are being implemented | Players can level up and gain more stats as they do
Iteration #6
Date of milestone | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23
Features in scope | More Enemies And Bosses | Sounds | More Levels | A Database Leaderboard | Lobby/Menu | Skills | Health Management
Features implemented | More Enemies And Bosses | Sounds | More Levels | A Database Leaderboard | Lobby/Menu |  | Health Management
Features in deficit this Iteration | [5 empty] | Skills
Iteration Comments & Summary | More Enemies and Bosses were implemented | Sounds can now be heard from the player and enemies and music plays in different areas | 3 New Areas added to explore with different enemies and bosses | Leaderboard is implemented with whover has slain the most bosses is at the top | After the login it now leads into a menu where you can create a lobby for other players to join and displays the leaderboard | Did not implement more skills for the player to play around with as I wanted to make interesting skills but that would have taken some time. | Added a limited heal that gets replenished at the respawn fountain, which allows players to heal during battle but at a cost.